## README
PIOS - حزمة قبول النشر المؤسسي
البند | الوصف
الغرض | تسجيل بيئة النشر، تنفيذ 24 فحص قبول، توثيق OIDC والنسخ والاستعادة، ودعم قرار Go/No-Go.
تنبيه | هذه الحزمة لا تثبت قبول مستشفى طريف قبل تعبئة الأدلة الحقيقية واعتمادها.
قاعدة التشغيل | أي فحص مطلوب بحالة Pending أوBlocked أوFail يمنع Go.
قاعدة الأمن | Dev Tokens وLocal Storage غير مقبولين في Pilot/Staging/Production.
قاعدة الاستعادة | وجود Backup دون Restore ناجح لا يحقق الفحص.
قاعدة الهوية | يلزم التحقق من issuer وaudience وJWKS والتوقيع والانتهاء وroles وsites.
الإصدار | Sprint 6 / Full Stack v0.7
تاريخ الإنشاء | 2026-08-01

## Environment
تعريف بيئة النشر والإصدار
Field | Value
Environment Code | tgh-pilot
Environment Name | Turaif PIOS Pilot
Environment Type | Pilot
Site Code | TGH
API Base URL
Frontend Base URL
Database | PostgreSQL 16
Object Storage | S3/MinIO Private
Auth Mode | OIDC
OIDC Issuer
Release Version | 0.7.0
Release SHA
TLS Enabled | FALSE
Monitoring Enabled | FALSE
Backup Policy Reference

## Acceptance_Checks
سجل فحوص قبول النشر - 24 فحصًا
Check Code | Category | Mode | Required | Expected | Status | Measured Value | Evidence Reference | Owner | Checked Date | Ready Flag
API_HEALTH | Platform | Automated | TRUE | API responds and exposes immutable release metadata | Pending |  |  |  |  | 0
DATABASE_REACHABLE | Database | Automated | TRUE | Database connection succeeds | Pending |  |  |  |  | 0
SCHEMA_TABLES_PRESENT | Database | Automated | TRUE | Expected 42-table model is present | Pending |  |  |  |  | 0
BASELINE_COUNTS_VALID | Data | Automated | TRUE | 41 standards, 266 MEs, 63 clauses, 75 documents, 12 UAT scenarios | Pending |  |  |  |  | 0
MIGRATIONS_APPLIED | Database | Manual | TRUE | Alembic head 0006 is applied | Pending |  |  |  |  | 0
OBJECT_STORAGE_CONFIGURED | Storage | Automated | TRUE | Production-like environment uses private S3-compatible storage | Pending |  |  |  |  | 0
OBJECT_STORAGE_PRIVATE_RW | Storage | Manual | TRUE | Private bucket write/read/delete test passes | Pending |  |  |  |  | 0
BACKUP_RESTORE_TESTED | Resilience | Manual | TRUE | Database and object restore test passes | Pending |  |  |  |  | 0
OIDC_MODE_ENABLED | Identity | Automated | TRUE | OIDC mode is enabled | Pending |  |  |  |  | 0
OIDC_DISCOVERY_JWKS | Identity | Manual | TRUE | Discovery and JWKS endpoints validate | Pending |  |  |  |  | 0
OIDC_TOKEN_VALIDATION | Identity | Manual | TRUE | Issuer, audience, signature and expiry validate | Pending |  |  |  |  | 0
OIDC_ROLE_SITE_CLAIMS | Identity | Manual | TRUE | Roles and TGH site claim enforce least privilege | Pending |  |  |  |  | 0
DEV_TOKENS_DISABLED | Security | Automated | TRUE | Development tokens are disabled | Pending |  |  |  |  | 0
TLS_ENABLED | Security | Automated | TRUE | TLS is enabled | Pending |  |  |  |  | 0
CORS_RESTRICTED | Security | Automated | TRUE | CORS excludes wildcard and local-only origins | Pending |  |  |  |  | 0
MONITORING_ENABLED | Operations | Automated | TRUE | Monitoring and alerting are enabled | Pending |  |  |  |  | 0
AUDIT_WRITE_PASS | Audit | Automated | TRUE | Audit trail is writable | Pending |  |  |  |  | 0
FRONTEND_URL_CONFIGURED | Frontend | Automated | TRUE | Public frontend URL is configured | Pending |  |  |  |  | 0
NOTIFICATION_SCHEDULER_PASS | Operations | Manual | TRUE | Scheduler executes without duplicate notifications | Pending |  |  |  |  | 0
EXPORT_RETENTION_PASS | Operations | Manual | TRUE | Export checksum and retention cleanup pass | Pending |  |  |  |  | 0
PILOT_USERS_READY | Pilot | Automated | TRUE | Eight required users are trained and access-tested | Pending |  |  |  |  | 0
P0_CAMPAIGN_READY | Pilot | Automated | TRUE | P0 campaign contains exactly 48 unique requests | Pending |  |  |  |  | 0
UAT_CRITICAL_PASS | Pilot | Automated | TRUE | All critical UAT scenarios pass | Pending |  |  |  |  | 0
FORMAL_GO_DECISION | Governance | Manual | TRUE | Authorized Go or ConditionalGo decision is recorded | Pending |  |  |  |  | 0

## Backup_Restore
اختبار النسخ الاحتياطي والاستعادة
Run Code | Status | Backup URI | Backup SHA-256 | Restore Target | RPO Seconds | RTO Seconds | Row/Object Count Summary | Evidence Reference | Executed Date
Acceptance Criteria | Pass requires successful isolated restore, matching row/object counts, intact links and audit continuity.
Database Counts | standards=41; measurable_elements=266; nested_clauses=63; documents=75
Object Storage | Evidence files and export objects restored with matching hashes
Authorization | Executed and approved by authorized platform/IT owners

## OIDC_Validation
التحقق من OIDC وClaims
Run Code | Issuer | Audience | Discovery | JWKS | Token | Claims | Observed Claims | Evidence Reference | Checked Date
|  |  | Pending | Pending | Pending | Pending
Required Claims | sub, email, name, roles, sites
Positive Test | Valid TGH user succeeds and receives mapped roles/site
Negative Test | Wrong audience/issuer or missing role/site is rejected
Secret Rule | Never store bearer tokens in the workbook or exported evidence
Acceptance | All four validation statuses must be Pass

## Evidence_Index
فهرس أدلة Go-Live المؤسسية
Evidence ID | Required Evidence | Owner | Status | Reference | Notes
E01 | Approved change ticket and release SHA | Platform Operations | Pending
E02 | Migration log through 0006 | SystemAdmin | Pending
E03 | Baseline validation 41/266/63/75/12 | AccreditationLead | Pending
E04 | Private object-storage probe | Platform Operations | Pending
E05 | Backup/restore report with RPO/RTO | Platform Operations | Pending
E06 | OIDC discovery, JWKS, token and claims validation | IT Security | Pending
E07 | TLS, CORS, secrets and monitoring evidence | IT Security | Pending
E08 | Scheduler and export-retention evidence | SystemAdmin | Pending
E09 | Turaif users, training and access tests | AccreditationLead | Pending
E10 | P0/ESR campaign with 48 requests | MedicationSafety | Pending
E11 | Critical UAT report and defect closure | UAT Lead | Pending
E12 | Formal Go/ConditionalGo decision | PharmacyDirector | Pending

## Go_NoGo
لوحة قرار قبول النشر
Indicator | Value | Decision | Rationale | Conditions | Approved By | Date
Checks Passed | 0 | NoGo
Checks Required | 24
Failed Required Checks | 0
Pending/Blocked Required | 24
Backup/Restore Status | Pending
OIDC Validation Status | Pending
Deployment Ready | NO
Recommended Decision | NoGo

## _Lists
CheckStatus | Decision | ValidationStatus | EnvironmentType
Pending | Go | Pending | Integration
Pass | ConditionalGo | Pass | Pilot
Fail | NoGo | Fail | Staging
Waived | Rollback |  | Production
Blocked